|  |  |  |
| --- | --- | --- |
| Actions | Done | To do |
| Traffic |  |  |
| Continue existing efforts to reduce speeding on Church Street, Frome Road, Back Lane, Kingston Lane and The Rank - (SID, Speed watch, traffic calming) | Councillor Simon Wager has coordinated 3 teams of Speed watch  Recruit and train more Speed watch volunteers  Cllr Simon Wager continues to operate SID rotation additional  Frome Road White Gates project  The Rank Crossroads white line to be reinstated.  Disciplining the traffic to drive on the correct side of the road would improve the safe for vehicles emerging from the rank.  The request to extend the existing warning lines around the bend by the church has been approved and the lining team are expecting to action the work imminently | Councillor Simon Wager Speed watch to continue (ongoing)  Councillor Simon Wager SID rotation (ongoing)  Councillor Simon Wager all projects completed with Wiltshire Council No further action required |
| Explore options to reduce speeding and improve safety on High Street, working with residents and Wiltshire Council (e.g., a new SID, Speed watch, improvements advised by highways) | 20mph speed limit under consultation and implemented | Councillor Simon Wager No action required moving forward |
| Publish regular data from the SID and Speed watch (e.g., in Newsletter, Noticeboards, Facebook) | Monthly report  Facebook posts by Parish Clerk | Councillor Simon Wager Regular reporting of information (ongoing) |
| Continue efforts to enforce weight limit (engagement with Wiltshire Council on A350/303, support of Weightwatchers) | Meeting has taken place at the Bradley Hare | Update meetings to take place with Wiltshire Council and MP  Councillors Simon Wager Susanna Brigden and Sebastian Seymour as and when required |
| Investigate long-term options to improve pavements (width, maintenance) and to create pavements where there are none (High Street, Frome Road) and identify budget cost. Present findings to the community. | Consultation with Highways actioned no suitable area to install footpaths/pavements High Street and Frome Road  Highways Engineer outcome reporting in the minutes and Parish News | No action required |
| Investigate options for bollards/railings to improve pavement safety and identify budget cost. Present findings to the community. | Consulted Highways Engineer outcome reporting in the minutes and Parish News | No action required |
| Investigate options for pedestrian crossing near the school bus pick up and identify budget cost. Present findings to the community. | Wiltshire Council Unitary Councillor Bill Parks consulted - Under zebra crossing (page 9) there is a section which indicates where Wiltshire Council highways use them and where Wiltshire Council Highways don't. i.e., they won't install zebra crossings where the 85th percentile speed exceeds 35mph or close to school entrances. The min threshold of 50 pedestrians crossing the road per hour over the 4 peak hours.  Typically, a zebra crossing including high friction surfacing on approaches costs between £21 – 34K  Unitary Councillor Bill Parks addressed Council regarding speed bumps/raised tables even being considered in the village  The noise and vibration that would arise from vehicles bouncing over them, particularly empty lorries would be intolerable for nearby properties and the sound would reverberate right through the village.  It would not be popular. On street parking spaces would also be lost and fronting properties would have to think very carefully about opening windows during the evening and early mornings.  The rattling noisy manhole cover that is currently causing much annoyance to the nearby property owners is a good example of the stress that is caused together with the deteriorating uneven road surface. | Wiltshire Council Criteria not reached minimum threshold not achievable noted  Noise from speed humps and loss of on street parking noted |
| Consider alternatives ways to fund long-term traffic related improvements to the village | Parish Council budgeting 25% contribution for all highways projects | Budget has been included for any future Highways projects. Sydenham’s development has highlighted Highways development monies to be spent in this area |
| Internet and mobile phone |  |  |
| Establish a volunteer group to investigate long-term options to have a mobile phone mast, considering practical options and health implications, and to explore options regarding improving internet to remote farms | New mast installed at the Village Hall working with the Estate | Project completed |
| Explore collaboration with The Deverills and any other relevant village to collaborate to get a mobile phone mast | Not required project progressed with Estate | Project completed |
| Communication |  |  |
| Continue to support the development and publication of the Parish Newsletter | Increased budget was allocated to support the Parish Newsletter | Ongoing support for parish newsletter funding at Budget discussions.  Including relevant articles in Parish news (on going) |
| Consider ways to improve visual/physical communication in the village via a Noticeboard e.g., print a monthly poster listing the standard activities in the village (e.g. first page of newsletter) and put in the Noticeboard | Poster of monthly events was created and printed and is available in the noticeboard. | Parishioner Volunteers no longer actioning the monthly listing of activites in the village. Village Hall Committee publishing a monthly report on the Facebook pages  No further action required |
| Encourage use of the Noticeboard for notices about various activities | Printed notice on Notice board directing Parishioners to contact the Clerk re placing notices adverts etc on the noticeboard | Ongoing |
| Annual village events |  |  |
| The PC will publish a list of the events and activities people have suggested | List was included in the plan and shared with Village Hall Committee | Village Hall Committee have taken ownership publishing events and activities no further action required |
| The PC will invite volunteers to organise the listed events, via a Volunteer Meeting in the hall (January), as well as putting a poster in the Newsletter and the Noticeboard, and approaching people who have expressed an interest | A volunteer evening was held at the Village Hall in January and approximately 20 people signed up to support different parish plan activities | Councillor to be assigned to work with and seek volunteers for any future projects |
| The PC will establish a Volunteer Group, coordinated by a Councillor/s, but populated by volunteers | Ian Ferguson took the lead in coordinating volunteer meetings and helped facilitate and organise a number of volunteer meetings (e.g. footpath group, village hall group, mobile phone, Bonfire night, Weightwatchers etc) but these groups were suspended due to covid (suspended) Ian Ferguson no longer a Councillor | New Lead Councillor to be assigned to seek volunteers for any future projects |
| The PC will prioritise investigating the feasibility of restarting two annual events in 2020 in the village, if community support is available, over the next 5 years:  - Bonfire Night (5 November); and  - Annual Summer Village Fete | Village Hall Committee taking ownership of Jubilee events and the village fete moving forward | Councillor Susanna Brigden regularly attends the meetings, in line with the constitution, as a community voice. |
| Village Shop |  |  |
| Share the comments and suggestions made in the consultation with the Village Hall Committee |  | Village Shop closed. Parishioner looking to develop the shop as a personal business. No further action required |
| Ask the Village Hall Committee to assess the feasibility of opening hours on a Saturday morning, given their reliance on volunteers, and to provide a response (Newsletter, Noticeboard, Facebook) | Village Hall concluded it was not feasible to open shop on Saturday (not enough volunteers) | Village Shop closed. No further action required |
| Support the Village Shop in its efforts to mobilise volunteers and to sustain the service it provides |  | Village Shop closed. No further action required |
| Village Hall |  |  |
| Share the comments and suggestions made in the consultation with the Village Hall Committee |  | Action completed |
| Ask the Village Hall Committee to assess the feasibility of any of the proposed ideas, and availability of willing volunteers, and to provide a response (Newsletter, Noticeboard, Facebook) |  | Village Hall Committee actioning their own consultation with the Community |
| Support the Village Hall with efforts to mobilise volunteers |  | Councillor Susanna Brigden lead Councillor |
| Footpaths and stiles |  |  |
| Work with the Wiltshire Rights of Way officer to assess and improve rights of way and permissive paths in MB  Hold a wider meeting with the responsible landowners/farmers and interested parishioners to discuss how to improve footpaths including signage, maintenance, stiles/gates and permissive paths | Council Officers will also be putting up Way Markers in Penny’s Wood and on MBRA3 where the Pheasant pen is.  Regarding the Pheasant pen there is still a large amount of work to be carried out.  • Pheasant pen needs to be removed – the farm tenants said this is something they will be able to do.  • The boardwalk will be moved onto the correct line by the Ramblers volunteer group, we will also look to improve the drainage in the boggy area.  • The correct line of the footpath will be waymarked to ensure walkers know where the correct line is. | Councillor Ann-Marie Halligan lead Councillor.  Estate and farmers moving forward with the project to improve the rights of way.  No further action required. |
| Support community efforts to establish a footpath maintenance group, with training from Wiltshire Rights of Way |  | Councillor Ann-Marie Halligan designated to lead Footpath group activities ongoing (in progress) |
| Continue to monitor and address maintenance and access to footpaths and respect for the Countryside Way |  | Ongoing activity by footpath group Councillor Ann-Marie Halligan designated to lead on the Rights of Way (ongoing) |
| Support community efforts to print and display a map of local walks in the Noticeboard | Village Hall Committee put up OS map inside the hall | Local Walks Leaflet in progress Councillor Esther Swan leading on the project. Draft still to be brought to Council |
| Investigate potential funding to improve stiles and gate access to local footpaths |  | Estate have communicated that they do not require AONB funding for the improvements. |
| Recreation ground |  |  |
| Establish a volunteer group to consider how to improve use and facilities at the existing recreation ground e.g. investigate the cost of an outdoor gym, playpark maintenance, dog exercise area |  | New Councillor to be designated to restart effort to create a volunteer group to discuss recreation area plans including outdoor gym  Include the under-18s in the volunteer group |
| Housing |  |  |
| Record and consider wishes expressed regarding the number, type and location of housing to be built in any future housing development |  | Parish Council to continue to be active in its comments for future developments (ongoing) |
| Share this information with Wiltshire Council planning department | Parish Plan sent to planning department | No further action required |
| Carbon footprint |  |  |
| Support community efforts to invite a relevant expert to give a talk on climate change and the environment |  | Council resolved that the Climate Group deal with this action. No further action to be taken by the Council |
| Seek advice from relevant expert authorities in local government and other organisations on what other similar communities are doing to reduce their carbon footprint | Parish Council made a climate change statement | Whole Council in its decision-making process (on going) |
| Investigate options regarding permissions for solar panels and wind turbines | Parish Clerk investigated and confirmed that declaration of climate emergency changes would not alter planning regulations for solar panels or wind turbines in MB (AONB; conservation zone) | Sign posting of Parishioners to information regarding Solar Panels and Wind Turbines on the Planning Portal and Wiltshire Council Planning Website. No further action required |
| The Church |  |  |
| Pass on suggestions about alternative use of the Church to the Church management and the Estate. Ask for their feedback on the feasibility of any of the ideas suggested | Parish plan shared with vicar and friends of the church | Councillor Milena Stancomb liaising with the PCC Committee |
| Support the Church’s efforts to mobilise volunteers for its maintenance |  | Councillor Milena Stancomb liaising with the PCC Committee |
| The pub |  |  |
| Ask the Estate to consider comments and suggestions by villagers about the pub as a social hub, in their commercial renovation plans |  | No further action required |
| Support the opening of the newly refurbished pub in 2020 |  | Public House refurbishment completed. No further action required |
| The bus service |  |  |
| Ensure information about The Link service is in the Newsletter, Noticeboard and Facebook | Efforts made to support promotion of The Link scheme | Councillor Simon Wager actioning a monthly News Item in the Parish News (ongoing) |
| Share the results of the survey with the bus company, highlighting request for a service to Frome at weekends, and ask about their plans for the service in the near future | Results shared- Wiltshire Council making a bid for further funding noted  <https://cms.wiltshire.gov.uk/%28S%28wmivcazpivfjfvvsgx0o2oaq%29%29/documents/s202892/Passenger-Transport-Service-Update-June%202022%20FINAL.pdf> | No further action required |
| Parish Council |  |  |
| Consider how to improve communication about the PC mandate – what it can and can’t do | Parish Clerk regularly submits to the Warminster Area Board Publications, Parish newsletter, Local Newspapers, Facebook pages and Noticeboard | (ongoing) |
| Consider how to improve communication between councillors and parishioners |  | Publish an update on the parish plan action plan yearly (ongoing) |
| Consider how to improve communication about the actions the PC undertakes each month | Councillors have written articles about relevant issues  Communications Policy in place | (ongoing) |
| Consider how to encourage parishioners to attend meetings | Participation in person encouraged at every meeting | Publish Parishioners right to attend and address Council on relevant publications, Website, Agendas, Minutes, Facebook posts and noticeboard |
| Conservation |  |  |
| Invite the Wiltshire Council Conservation Officer and/or AONB expert to give a talk on planning in a conservation area/AONB | The Parish Clerk actioned invite relevant expert from WC or AONB to give a talk in the village hall. | AONB highlighted link to their website  Planning Portal re conservation area Advertised Website page re planning No further action |
| Support community efforts to provide public information (event, print, online) about the vernacular architectural style of the village and local historical features | Volunteer group expressed interest | New Councillor to be assigned to restart this project |
| Investigate options to maintain and highlight local historical features | Interpretation board Project completed | New Councillor to be assigned to restart efforts to explore potential of plaques/signs to be put up at historic sites in the village |
| Police and crime |  |  |
| Pass on survey comments regarding rural crime and satisfaction with the police response to the relevant police authority | Parish plan shared with PCSO | No ongoing action required |
| Ask the Community Police officer to share examples of how communities can protect against rural crime | Alert scheme published in parish newsletter and on Facebook | Facebook pages to continue to publish police news alerts |
| Rural tourism |  |  |
| Support efforts to include more visible/physical information in the village about monthly events and activities in the village, local footpaths, attractions, and local history (e.g. Noticeboard, Facebook, Newsletter online) | Activities to maintain rural beauty of the village - volunteers have weeded and strimmed paths, painted railings, made Christmas wreaths  Spring bulb planting  Village map (painted/info board with historic sites, paths etc) actioned | Litter pick (planned yearly)  Village Hal Committee promoting and providing activites for Parishioners e.g., Christmas window decorations |
| Support efforts to recognise village’s strategic position on national cycle route 25 e.g. signage, facilities for cyclists | Volunteer wrote article about cycling in the village newsletter  Parish Council reported improvements needed on national cycle route | Cycling to be considered for all future planning applications. Wiltshire Council Report an issue app to be highlighted to parishioners for road conditions to be reported directly |
| Under-18s |  |  |
| Support efforts by young people in the village to liaise with the parish council and village hall regarding their ideas, activities and events for the village (e.g. via a youth council, an organised group or ad-hoc form of communication as they suggest)  Ensure under-18s views are consulted as part of all the relevant initiatives conducted in the parish plan | Under-18s gave a presentation at the parish plan consultation meeting  Under-18s attended parish council to set out their key interests | Councillor Esther Swan the under 18s Representative for any relevant issues and questions |
| Investigate concerns raised about sixth form travel costs with Wiltshire Council and report back | Wiltshire Council confirmed that those families that were eligible did receive additional help with the costs. | No further action required |
| Include in work on traffic concerns raised by children about impact of HGVs and heavy traffic on safety when catching the school bus | The PC to ask the under-18s to collate and record comments and experiences of traffic safety when walking to get the school bus.  PC to share these findings with relevant authorities. | Councillor Milena Stancomb & Under 18s Representative Esther Swan  Weight Watchers group covering this area |